## Sheet1
Review Due/Status	Document	Type of Review	Review Summary	Revision Due	Start WGLC	WGLC Target	IESG Target	Editor:	Chair reviewer:	Reviewer 1:	Reviewer 2:	Reviewer 3:	Reviewer 4:	Reviewer 5:	Reviewer 6:	Reviewer 7:	Reviewer 8:	Reviewer 9:	Notes:
07-12-24	draft-ietf-sipping-overload-reqs-01	Post-WGLC		08-01-14	07-04-30	07-05-21	08-01-31	Jonathan Rosenberg	Mary Barnes	Volker Hilt	Spencer Dawkins	Tolga Asveren
Awaiting Update	draft-ietf-sipping-service-identification-00.txt	Initial Review	Right track; issues	07-11-19	08-01-10	08-01-31	08-05-31	Jonathan Rosenberg	Gonzalo Camarillo	Tolga Asveren	Mahesh	RAI (Spencer Dawkins)	APPS (Claudio Allocchio)						Doc is undergoing APPS and RAI area reviews
Awaiting Update	draft-ietf-sipping-media-policy-dataset-05	Post-WGLC		08-01-14	07-05-21	07-06-11	08-02-28	Volker Hilt	Mary Barnes	Roni Even	Jari Urpalainen	Christian Schmidt
Awaiting Update	draft-ietf-sipping-sip-offeranswer-04.txt	Post-WGLC		07-12-21	07-08-30	07-09-30	08-01-31	T. Sawada	Mary Barnes	Byron Campen	Jonathan Rosenberg	Rajeev Seth	B, Nataraju
Awaiting Update	draft-ietf-sipping-cc-transfer-08	Post-WGLC		07-09-30	Completed	Completed	08-03-31	Alan Johnston	Gonzalo Camarillo										Waiting on GRUU
Awaiting Update	draft-ietf-sipping-nat-scenarios-07	Pre-WGLC	Right track; issues	07-10-15	07-12-17	08-01-14	08-03-31	Chris Boulton	Mary Barnes	Guarav Kuhlshreshtha	Vijay Gurbani	Spencer Dawkins							Shifting IESG target due to ICE dependency.
Completed	draft-ietf-sipping-service-examples-13.txt	AD	Ready	Completed	06-05-11	06-07-01	07-09-30	Alan Johnston	Gonzalo Camarillo	Vijay Gurbani	John Elwell	Joel Repiquet		Chandra Ravipati	Eric Burger		Miguel Garcia
Completed	draft-ietf-sipping-v6-transition-04.txt	AD	Right track; issues	Completed	06-06-26	06-07-17	06-09-14	Vijay Gurbani	Mary Barnes	Francois Audet	Dale Worley
Completed	draft-ietf-sipping-capacity-attribute-04.txt	AD	Ready; ?/nits	Completed	06-09-05	06-09-19	06-11-30	Gonzalo Camarillo	Mary Barnes	Brian Stucker									Depends on URI list stuff
Completed	draft-ietf-sipping-dialogusage-05	AD	Right track; issues	Completed	06-09-11	06-10-02	07-01-31	Robert Sparks	Gonzalo Camarillo	Paul Kyzivat	Derek MacDonald	IVijay Gurbani	Francois Audet
Completed	draft-ietf-sipping-pending-additions-02.txt	AD	Ready	Completed	06-09-26	06-10-17	07-03-31	Gonzalo Camarillo	Mary Barnes	Ben Campbell
Completed	draft-ietf-sipping-consent-format-03.txt	AD	Ready	Completed	06-09-26	06-10-17	07-03-31	Gonzalo Camarillo	Mary Barnes	Ben Campbell
Completed	draft-ietf-sipping-sbc-funcs-03.txt	AD	Ready	Completed	06-11-29	06-12-20	07-05-31	Jani Hautakorpi	Mary Barnes	Michael Procter	Francois Audet	Spencer Dawkins
Completed	draft-ietf-sipping-spam-04	AD	Ready	Completed	06-12-11	06-12-31	07-03-31	Jonathan Rosenberg	Gonzalo Camarillo	Vijay Gurbani
Completed	draft-ietf-sipping-race-examples-04.txt	AD	Ready	Completed	07-04-23	07-05-14	07-09-30	M Hasebe	Gonzalo Camarillo	Vijay Gurbani	Dale Worley	Anders Kristensen
Completed	draft-ietf-sipping-toip-07.txt	AD	-04:Respositioning proposed, -05: Ready	Completed	Completed	Completed	06-08-30	Arnoud Van Wijk	Mary Barnes	Tom Taylor		-							-05 version addresses detailed WG review comments
Completed	draft-ietf-sipping-rtcp-summary-01	AD		Completed	Completed	Completed	Completed	Amy Pendleton	Gonzalo Camarillo
Completed	draft-ietf-sipping-ipv6-torture-tests-03	AD	Ready	Completed	Completed	Completed	07-05-17	Vijay Gurbani	Gonzalo Camarillo	B, Nataraju	AC Mahendran
Completed	draft-ejzak-sipping-p-em-auth-03.txt	AD	Ready	Completed	N/A	N/A	07-01-31	Richard Ejzak	Gonzalo Camarillo	Aki Niemi	Yaron Pdut
Completed	draft-camarillo-sipping-profile-key-01.txt	AD	Ready	Completed	N/A	N/A	N/A	Gonzalo Camarillo	Mary Barnes	Miguel Garcia
Completed	draft-ietf-sipping-transc-framework-04.txt	Editor Q			Completed	Completed	Completed	Gonzalo Camarillo	Mary Barnes
Completed	draft-ietf-sipping-transc-conf-03.txt	Editor Q			Completed	Completed	Completed	Gonzalo Camarillo	Mary Barnes
Completed	draft-allen-sipping-poc-p-answer-state-header-03	Editor Q	Ready	None needed.	N/A	N/A	N/A	Andrew Allen	Gonzalo Camarillo		-	-
Completed	draft-hautakorpi-sipping-uri-list-handling-refused-02.txt	Expert Review	Ready	Completed	N/A	N/A	07-08-30	Jani Hautakorpi	Mary Barnes	Tom Hiller
Completed	draft-ietf-gruu-reg-event-08	IESG	Ready		Completed	Completed	Completed (May 2006)	Paul Kyzivat	Mary Barnes	Brian Stucker	Jonathan Rosenberg
Completed	draft-ietf-sipping-uri-services-06.txt	IESG		Completed	Completed	Completed	Completed	Gonzalo Camarillo	Mary Barnes										Awaiting Consent FW
Completed	draft-ietf-sipping-cc-framework-08.txt	Post-WGLC	Ready with nits	Completed	07-03-16	07-04-13	07-12-31	Alan Johnston	Gonzalo Camarillo	Sriram Parameswar	AC Mahendran	John Elwell	Xavier Marjou
Completed	draft-ietf-sipping-policy-package-04	Post-WGLC	Ready	Completed	07-05-21	07-06-11	08-02-28	Volker Hilt	Mary Barnes	Bob Penfield	Shida Schubert	Flemming Andreasen	Roni Even
Completed	draft-ietf-sipping-config-framework-14.txt	Post-WGLC	Right track; issues	Completed	07-06-04	07-06-25	07-12-31	Sumanth Channabasappa	Mary Barnes	Roni Even	John Elwell	Shida Schubert	Dave Robbins
Moved to SIP	draft-ietf-sipping-session-policy-framework-00	Initial Review		Completed	06-11-09	06-11-30	07-01-31
Moved to SIP	draft-ietf-sipping-consent-framework-04.txt	Post-WGLC		Completed	06-08-03	06-08-31	06-10-31
Moved to SIP	draft-ietf-sipping-uri-list-subscribe-05.txt	Post-WGLC		Completed	Completed	Completed	06-10-31
Moved to SIP	draft-ietf-sipping-uri-list-message-07.txt	Post-WGLC		Completed	Completed	Completed	06-10-31
Moved to SIP	draft-ietf-sipping-uri-list-conferencing-05.txt	Post-WGLC		Completed	Completed	Completed	06-10-31
Moved to SIP	draft-ietf-sipping-multiple-refer-05.txt	Post-WGLC		Completed	Completed	Completed	06-10-31
Re-Review	draft-vanelburg-sipping-served-user-02.txt	Expert Review	Almost ready		N/A	N/A	N/A	J Van Elberg	Gonzalo Camarillo	Spencer Dawkins
Re-Review	draft-ejzak-sipping-p-em-auth-00.txt	Expert Review	Ready with issues/nits	Completed	N/A	N/A	N/A	Richard Ejzak	Gonzalo Camarillo	Aki Niemi
Re-Review	draft-ietf-sipping-config-framework-08.txt	IESG	Right track; issues	Completed	06-10-10	06-10-31	06-12-31	Dan Petrie	Gonzalo Camarillo	Roni Even	Amy Pendleton	Martin Dolly	Christian Stredicke						OMA Critical
Re-Review	draft-ietf-sipping-policy-package-01	Initial Review	Right track; issues	Completed	06-11-09	06-11-30	07-01-31	Volker Hilt	Mary Barnes	Bob Penfield	Alan Hawrylyshen	Flemming Andreasen	Roni Even	Shida Schubert
Re-Review	draft-ietf-sipping-media-policy-dataset-01	Initial Review	Ready with issues/nits	Completed	06-11-09	06-11-30	07-01-31	Volker Hilt	Mary Barnes	Bob Penfield	Alan Hawrylyshen	Flemming Andreasen	Roni Even	Shida Schubert
Re-Review	draft-ietf-sipping-config-framework-10.txt	Initial Review	Right track; issues	Completed	07-05-01	07-05-22	07-08-31	Sumanth Channabasappa	Mary Barnes	Design Team
Re-Review	draft-ietf-sipping-config-framework-11.txt	Interim Review	Right track; issues	Completed	07-05-01	07-05-22	07-08-31	Sumanth Channabasappa	Mary Barnes	John Elwell	Cullen Jennings	Adam Roach	EKR
Re-Review	draft-ietf-sipping-config-framework-09.txt	Post-WGLC	Needs serious editorial work	Completed	06-10-10	06-10-31	06-12-31	Dan Petrie	Mary Barnes	Roni Even	Francois Audet	Martin Dolly	Sumanth Channabasappa
Re-Review	draft-ietf-sipping-sbc-funcs-00.txt	Post-WGLC	Right track; issues	Completed	06-11-29	06-12-20	07-02-28	Jani Hautakorpi	Mary Barnes	Michael Procter	Brian Stucker	Spencer Dawkins	Francois Audet
Re-Review	draft-ietf-sipping-sbc-funcs-01.txt	Post-WGLC	Almost ready	Completed	06-11-29	06-12-20	07-05-31	Jani Hautakorpi	Mary Barnes	Michael Procter	Francois Audet	Spencer Dawkins
Re-Review	draft-ietf-sipping-spam-03	Post-WGLC	Right track; issues	Completed	06-12-11	06-12-31	07-02-28	Jonathan Rosenberg	Gonzalo Camarillo	Vijay Gurbani	Geoffrey Dawirs	Shida Schubert
Re-Review	draft-ietf-sipping-ipv6-torture-tests-01	Post-WGLC	Right track; issues	Completed	07-03-09	07-04-06	07-07-31	Vijay Gurbani	Gonzalo Camarillo	B, Nataraju	AC Mahendran
Re-Review	draft-ietf-sipping-race-examples-01.txt	Post-WGLC	Right track; issues	Completed	07-04-23	07-05-14	07-08-31	M Hasebe	Gonzalo Camarillo	Vijay Gurbani	Dale Worley	Anders Kristensen
Re-Review	draft-ietf-sipping-media-policy-dataset-04	Post-WGLC	Right track; issues	Completed	07-05-21	07-06-11	07-10-31	Volker Hilt	Mary Barnes	Roni Even	Jari Urpalainen	Christian Schmidt
Re-Review	draft-ietf-sipping-config-framework-13.txt	Post-WGLC	Right track; issues	Completed	07-06-04	07-06-25	07-11-30	Sumanth Channabasappa	Mary Barnes	Roni Even	John Elwell	Shida Schubert	Dave Robbins
Re-Review	draft-ietf-sipping-config-framework-12.txt	Post-WGLC	Needs editorial work	Completed	07-06-04	07-06-25	07-11-30	Sumanth Channabasappa	Mary Barnes	Roni Even	John Elwell	Shida Schubert	Dave Robbins
Re-Review	draft-ietf-sipping-overload-reqs-00	WGLC	Almost ready; nits/comments	Completed	07-04-30	07-05-21	07-10-31	Jonathan Rosenberg	Mary Barnes	Volker Hilt	Spencer Dawkins	Tolga Asveren
Re-Review	draft-ietf-sipping-sip-offeranswer-03.txt	WGLC	Right track;minor issues/nits	Completed	07-08-30	07-09-30	08-01-31	T. Sawada	Mary Barnes	Byron Campen	Jonathan Rosenberg	Rajeev Seth	B, Nataraju
Review Comp	draft-camarillo-sipping-profile-key-00.txt	Expert Review	Right track; issues	Completed	N/A	N/A	N/A	Gonzalo Camarillo	Mary Barnes	Miguel Garcia
Review Comp	draft-ietf-sipping-service-examples-10.txt	Post-WGLC	Right track; issues	Completed	06-05-11	06-07-01	06-11-30	Alan Johnston	Gonzalo Camarillo	Vijay Gurbani	John Elwell	Joel Repiquet	Nagesh Kumar	Chandra Ravipati	Eric Burger	Jeroen Bemmel	Miguel Garcia	Dale Worley
Review Comp	draft-ietf-sipping-pending-additions-00.txt	Post-WGLC	Ready with nits	Completed	06-09-26	06-10-17	06-10-31	Gonzalo Camarillo	Mary Barnes	Ben Campbell	Shida Schubert	Chris Boulton	AC Mahendran						WGLC at the same time as consent FW in SIP WG
Review Comp	draft-ietf-sipping-pending-additions-01.txt	Post-WGLC	Ready; template nits	Completed	06-09-26	06-10-17	07-03-31	Gonzalo Camarillo	Mary Barnes	Ben Campbell
Review Comp	draft-ietf-sipping-consent-format-01.txt	Post-WGLC	Ready; template nits	Completed	06-09-26	06-10-17	07-03-31	Gonzalo Camarillo	Mary Barnes	Ben Campbell
Review Comp	draft-ietf-sipping-consent-format-00.txt	Post-WGLC	Right track; issues	Completed	06-09-26	06-10-17	06-10-31	Gonzalo Camarillo	Mary Barnes	Ben Campbell	Shida Schubert	Chris Boulton	AC Mahendran						WGLC at the same time as consent FW in SIP WG
	-	New			07-12-31	07-12-31
	-	New			07-12-31	07-12-31