## Sheet1
Review Due/Status	Document	Type of Review	Review Summary	Revision Due	Start Review	Start WGLC	WGLC Target	IESG Target	Editor:	Chair reviewer:	Reviewer 1:	Reviewer 2:	Reviewer 3:	Reviewer 4:	Reviewer 5:	Reviewer 6:	Reviewer 7:	Reviewer 8:	Reviewer 9:	Notes:
08-11-27	draft-ietf-sipping-nat-scenarios-09	Post-WGLC		09-03-21	09-03-30	08-05-01	08-05-23	09-06-30	Chris Boulton	Mary Barnes	Francois Audet	Vijay Gurbani	Dan Wing	Ali Keranen	Jerry Yin	Philip Matthews	Behave (Remi Denis-Courmant)			Shifting IESG target due to TURN dependency.
08-12-31	draft-wing-sipping-srtp-key-04	Early Review – SecDir		09-05-04	08-11-06	TBD	TBD	TBD	Dan Wing	Gonzalo Camarillo	Eric Rescorla (Sec-Dir)
09-02-23	draft-ietf-sipping-presence-scaling-requirements-03.txt	Post-WGLC		09-03-09	09-03-09	08-08-13	08-09-03	09-03-30	Avshalom Houri	Gonzalo Camarillo	Vijay Gurbani		Hisham Khartabil	Jean-Francois Mule
Awaiting Other Doc	draft-ietf-sipping-media-policy-dataset-06	Pre-WGLC2		09-03-09	09-04-30	09-04-30	09-05-20	09-09-30	Volker Hilt	Mary Barnes	Roni Even	Jari Urpalainen	Christian Schmidt							Doc has a dependency on core profile dataset draft and will be progressed with that doc
Awaiting Solution Doc(s)	draft-ietf-sipping-sip-offeranswer-10.txt	Pre-WGLC2		09-07-05	09-08-17	09-08-17	09-08-31	09-12-31	Paul Kyzivat	Mary Barnes	Byron Campen	Jonathan Rosenberg	Rajeev Seth	B, Nataraju						Dependency on solutions in SIP WG. -09=AD comments, -10=conversion to XML, -11=Gen-ART
Awaiting Update	draft-sinnreich-sip-tools-04.txt	Expert Review		09-03-09	09-03-10	N/A	N/A	N/A	Henry Sinnreich	Mary Barnes	Paul Kyzivat (RAI)
Awaiting Update	draft-niemi-sipping-event-throttle-07.txt	Pre-WGLC		09-02-27	09-03-02	09-04-20	08-05-11	09-08-30	Salvatore Loreto	Mary Barnes	Brian Rosen	Hisham Khartabil	Dale Worley
Awaiting Update	draft-ietf-sipping-profile-dataset-01.txt	Pre-WGLC	Right track; issues	09-02-20	09-02-23	09-04-30	09-05-20	09-09-30	Martin Dolly/Dale Worley	Mary Barnes	Jean-Luc Bakker	Andrew Hutton	Dale Worley
Awaiting Update	draft-ietf-sipping-overload-design-00	Pre-WGLC		09-03-09	08-03-16	09-05-23	09-06-16	09-10-31	Volker Hilt	Mary Barnes
Awaiting Update	draft-johnston-sipping-cc-uui-06	WGLC		09-02-13	09-02-16	09-02-16	09-03-02	N/A (SIP WG)	Alan Johnston	Gonzalo Camarillo	Vijay Gurbani	Keith Drage	Laura Liess	Spencer Dawkins
Completed	draft-ietf-sipping-sbc-funcs-03.txt	AD	Ready	Completed	Completed	06-11-29	06-12-20	07-05-31	Jani Hautakorpi	Mary Barnes	Michael Procter	Francois Audet	Spencer Dawkins
Completed	draft-ietf-sipping-cc-framework-10.txt	AD	Ready with nits	Completed	Completed	07-03-16	07-04-13	08-04-30	Alan Johnston	Gonzalo Camarillo	Xavier Marjou	John Elwell	AC Mahendran
Completed	draft-ietf-sipping-policy-package-04	AD	Ready	Completed	Completed	07-05-21	07-06-11	08-02-28	Volker Hilt	Mary Barnes	Bob Penfield	Shida Schubert	Roni Even
Completed	draft-ietf-sipping-config-framework-15.txt	AD	Right track; issues	Completed	Completed	07-06-04	07-06-25	08-02-28	Sumanth Channabasappa	Mary Barnes	Roni Even	John Elwell	Shida Schubert	Dave Robbins
Completed	draft-ietf-sipping-service-identification-03.txt	AD	Ready	Completed	Completed	08-03-27	08-04-11	08-09-30	Jonathan Rosenberg	Gonzalo Camarillo	Tolga Asveren	Mahesh	RAI (Spencer Dawkins)	Paul Kyzivat
Completed	draft-ietf-sipping-update-pai-09.txt	AD		Completed	Completed	08-10-02	08-10-23	08-12-31	John Elwell	Gonzalo Camarillo	Vijay Gurbani	Paul Kyzivat	Francois Audet	Thomas Stach	Mailing list thread
Completed	draft-ietf-sipping-rtcp-summary-01	AD		Completed	Completed	Completed	Completed	Completed	Amy Pendleton	Gonzalo Camarillo			-
Completed	draft-ietf-sipping-cc-transfer-08	AD		Completed	Completed	Completed	Completed	08-03-31	Alan Johnston	Gonzalo Camarillo
Completed	draft-ietf-sipping-v6-transition-04.txt	Editor Q	Right track; issues	Completed	Completed	06-06-26	06-07-17	06-09-14	Vijay Gurbani	Mary Barnes	Francois Audet	Dale Worley
Completed	draft-andreasen-sipping-rfc3603bis-07	Editor Q	Ready	Completed	Completed	N/A	N/A	N/A	Fleming Andreasen	Mary Barnes	Miguel Garcia
Completed	draft-drage-sipping-service-identification-02.txt	IESG (Ind/AD)	Right track; issues	Completed	Completed	N/A	N/A	Completed	Keith Drage		Review Comments Summary		Andrew Allen
Completed	2008 Reviews
Completed	2006-2007-Reviews
Re-Review	draft-ietf-sipping-sip-offeranswer-08.txt	AD/Back in WG		Completed	Completed	07-08-30	07-09-30	08-04-30	T. Sawada	Mary Barnes	Byron Campen	Jonathan Rosenberg	Rajeev Seth	B, Nataraju
Re-Review	draft-sinnreich-sip-tools-03.txt	Expert Review		Completed	Completed	N/A	N/A	N/A	Henry Sinnreich	Mary Barnes	Paul Kyzivat (RAI)
Re-Review	draft-ietf-sipping-nat-scenarios-07	Initial Review	Right track; issues	Completed	Completed	08-05-06	08-05-27	08-07-31	Chris Boulton	Mary Barnes	Guarav Kuhlshreshtha	Vijay Gurbani	Spencer Dawkins
Re-Review	draft-ietf-sipping-presence-scaling-requirements-00.txt	Initial Review	Ready with nits	Completed	Completed	08-08-04	08-08-25	08-11-30	Avshalom Houri	Gonzalo Camarillo	Vijay Gurbani
Re-Review	draft-ietf-sipping-nat-scenarios-08	WGLC	Right track; issues	Completed	TURN IETF LC	08-05-01	08-05-23	09-03-31	Chris Boulton	Mary Barnes	Francois Audet	Vijay Gurbani	Dan Wing	Ari Keranen	Jerry Yin	RAI (Phillip Matthews)	Behave (Remi Denis-Courmant)			Shifting IESG target due to TURN dependency.
Re-Review	draft-ietf-sipping-presence-scaling-requirements-01.txt	WGLC	Right track; issues	Completed	Completed	08-08-13	08-09-03	08-11-30	Avshalom Houri	Gonzalo Camarillo	Vijay Gurbani		Hisham Khartabil	Jean-Francois Mule	Christian Schmidt
Re-Review	draft-ietf-sipping-presence-scaling-requirements-02.txt	Post-WGLC	Almost Ready	Completed	Completed	08-08-13	08-09-03	09-03-30	Avshalom Houri	Gonzalo Camarillo	Vijay Gurbani		Hisham Khartabil	Jean-Francois Mule
	-	New				08-12-31	08-12-31
	-	New				08-12-31	08-12-31