## Sheet1
Document Title | Status | WG Item | Priority
draft-ietf-sip-100rel-02.txt | IESG review -- Mankin | Yes | high
draft-ietf-sip-callerprefs-02.txt | IETF49, Possily ready for WGLC, moderate commit. WGLC 24Dec00 | Yes | high
draft-ietf-sip-call-flows-02.txt | IETF49, small changes requested, add and ready for WGLC | Yes | high
draft-ietf-sip-guidelines-01.txt | WGLC exp 24Dec00 | Yes | high
draft-ietf-sip-isup-mime-07.txt | Reissued from WGLC nits 18Jan01, ready for IESG | Yes | high
draft-ietf-sip-manyfolks-resource-00.txt | IETF49, dependencies on 2543-bis to resolve, standards track | Yes | high
draft-ietf-sip-mib-01.txt | IETF49, update planned for 2001, finalize IETF50 | Yes | high
draft-ietf-sip-serverfeatures-02.txt | IESG returned to WG | Yes | high
draft-ietf-sip-service-examples-00.txt | IETF49, further work needed | Yes | high
draft-ietf-sip-session-timer-04.txt | Ready for WG Last Call, high commit at IETF 49 | Yes | high
draft-ietf-sip-cc-transfer-02.txt | IETF49, further discussion needed, target for WGLC by end of Jan00 | Yes | high
draft-ietf-sip-rfc2543bis-02.txt | standards track to replace 2543 | Yes | high
draft-ietf-sip-call-auth-00.txt | IETF49 -- convert to individual with WG concurrence, send to IESG on informational track | Yes | low
draft-ietf-sip-state-00.txt | IETF49 -- ready for WGLC | Yes | low
draft-ietf-sip-privacy-00.txt | IETF49, depends on 2543-bis, standards track | Yes | medium
draft-ietf-sip-dhcp-01.txt | Returned to HGS, still working as of 3Jan01. Issues with underscores. | Yes
draft-ietf-sip-srv-00.txt | HGS working, ready early 2001 | Yes
draft-camarillo-3pcc-qos-00.txt | IETF49, need to combine with other AAA | No | high
draft-camarillo-sip-isup-bcp-00.txt | IETF49, little discussion | No | high
draft-gearhart-sip-deaf-req-00.txt | IETF49 - high consensus as WG work effort | No | high
draft-lennox-sip-reg-payload-01.txt | IETF49, consensus to adopt | No | high
draft-roach-sip-subscribe-notify-02.txt | IETF49, some issues | No | high
draft-rosenberg-sip-entfw-00.txt | IETF49, little discussion | No | high
draft-vemuri-sip-t-context-01.txt | IETF49, use as SIP-T umbrella draft | No | high
draft-rosenberg-sip-app-components-00.txt | IETF49, little discussion | No | high
draft-rosenberg-sip-conferencing-models-00.txt | IETF49, little discussion | No | high
draft-byerly-sip-hide-route-00.txt | IETF49, little discussion | No | low
draft-byerly-sip-radius-00.txt | IETF49, little discussion | No | low
draft-dcsgroup-sip-proxy-proxy-03.txt | IETF49 - Ready for IESG as ind. informational with WG concurrence. | No | low
draft-dean-phonectl-03.txt | Revised 11Jan01, no home WG | No | low
draft-hamer-sip-session-auth-00.txt | IETF49, need to combine with other auth work | No | low
draft-gross-cops-sip-00.txt | IETF49 - Move to other wg? | No | medium
draft-gross-sipaq-00.txt | IETF49 - move other wg? | No | medium
draft-johnston-sip-osp-token-01.txt | IETF49, publish as ind. | No | medium
draft-lennox-sip-cgi-04.txt | Proceeeding as individual | No | medium
draft-levy-sip-diversion-01.txt | IETF49, discussion to list | No | medium
draft-agrawal-roy-palawat-sip-h323-interworking-00.txt |  | No
draft-biggs-sip-nat-00.txt |  | No
draft-biggs-sip-replaces-00.txt |  | No
draft-calhoun-sip-aaa-reqs-01.txt |  | No
draft-camarillo-manyfolks-confirm-00.txt |  | No
draft-camarillo-sip-sdp-01.txt |  | No
draft-campbell-sip-cc-framework-01.txt |  | No
draft-campbell-sip-e164-00.txt |  | No
draft-campbell-sip-service-control-01.txt | Submitted to IESG. Token (Mankin, reminder sent 3Jan01) | No
draft-choudhuri-sip-info-digit-00.txt |  | No
draft-culpepper-sip-info-event-00.txt | Dead | No
draft-dcsgroup-sip-arch-03.txt |  | No
draft-dean-handoff-00.txt | Initial draft 18Jan01, on Call control | No
draft-dean-phonectl-02.txt |  | No
draft-deason-sip-soap-00.txt |  | No
draft-itsumo-sip-mobility-multimedia-00.txt |  | No
draft-itsumo-sip-mobility-req-02.txt |  | No
draft-itsumo-sip-mobility-service-00.txt |  | No
draft-itsumo-sip-mobility-tcp-00.txt |  | No
draft-jfp-sipfw-policy-00.txt |  | No
draft-kempf-sip-findsrv-00.txt |  | No
draft-lebovits-sip-in-00.txt |  | No
draft-mahy-sip-189-00.txt |  | No
draft-mahy-sip-message-waiting-00.txt |  | No
draft-mahy-sip-peer-3pcc-00.txt |  | No
draft-mark-sip-dmcs-00.txt |  | No
draft-moyer-sip-appliances-framework-01.txt |  | No
draft-mule-sip-t38callflows-00.txt |  | No
draft-nishigaya-sip-ccpp-00.txt |  | No
draft-odoherty-root-sip-servlet-00.txt |  | No
draft-odoherty-sip-java-enhanced-00.txt |  | No
draft-odoherty-sip-servlet-delivery-00.txt |  | No
draft-oran-sip-visited-00.txt |  | No
draft-polk-sip-mlpp-mapping-00.txt |  | No
draft-roach-sip-acb-00.txt |  | No
draft-roach-voip-ringtone-00.txt |  | No
draft-rosenberg-sip-3pcc-01.txt | IETF49 Controversial, further list discussion needed | No
draft-rosenberg-sip-firewalls-00.txt |  | No
draft-rosenberg-sip-hearingimpaired-00.txt |  | No
draft-rosenberg-sip-sctp-00.txt |  | No
draft-schulzrinne-sin-01.txt |  | No
draft-schulzrinne-sip-911-00.txt |  | No
draft-schulzrinne-sip-register-00.txt |  | No
draft-singh-sip-h323-01.txt |  | No
draft-sinnreich-aaa-interdomain-sip-qos-osp-00.txt |  | No
draft-sinnreich-interdomain-sip-qos-osp-01.txt |  | No
draft-thernelius-sip-firewall-solution-00.txt |  | No
draft-thomas-sip-mime-osp-token-00.txt |  | No
draft-tsang-sip-appliances-do-00.txt |  | No
draft-van-doorselaer-sip-xcast-00.txt |  | No
draft-agrawal-sip-h323-interworking-reqs-00.txt | Planned for info 31Jan01 | N/A | N/A